## Sheet1
Annex A. Expenditure data collection work plan – requirements, deliverables and benefits
Ref | Deliverable | Benefits | Timeline
Response rates
1 | Assessment of higher levels of conditional incentive on LCF response rates. | Cost and benefit analysis will inform future response rate strategy. | January 2019 – initial analysis. Project end date dependent on achieved sample size and findings from initial analysis.
2 | An assessment of the impact of falling response rates on data quality. | Users informed of changes to data quality. Inform direction of future response rate strategy. | Spring 2019
Development of expenditure questionnaire
3 | Impact assessment of FYE 2019 expenditure questionnaire changes on estimates. | Users informed of impact of questionnaire changes. | Throughout FYE 2019
4 | Review and development of priority expenditure topics leading to implementation of questionnaire changes in April 2019. | Expenditure questionnaire keeps pace with changes in spending habits of households. | September 2018 to March 2019
Development of LCF diary
5 | Redesign of the LCF paper diary, including qualitative and quantitative testing. | At point of implementation: - reduction in respondent and interviewer burden - improved data quality | To be confirmed – dependent on available resource and funding
6 | Identification, development and testing of options for electronic method(s) to modernise paper diary. | Once implemented: - reduction in interviewer costs - reduction in respondent burden | To be confirmed – dependent on available resource and funding
Development of optical character recognition from scanned receipts and automatic COICOP coding
7 | Development of optical character recognition and automated COICOP coding- including an assessment of time and cost savings. | Implementation of a more efficient processing system, leading to increased timeliness of data delivery. | September 2018 to December 2019