## Sheet1
Milestone | Date* | Description | Status
Last publication of Census 2021 articles | Summer 2025 | The last in a series of analytical articles giving insight into Census 2021 data is published | Updated 24 May 2022
Final release of Census 2021 outputs | Winter 2023 | Publish final data from Census 2021 for England and Wales. | Successfully completed
First publication of Census 2021 analysis articles | Spring 2023 | The first in a series of analytical articles giving insight into Census 2021 data is published | Successfully completed
Publication of first results | 28 June 2022 | The first results from Census 2021 are published. | Successfully completed
National Statistics accreditation of Census 2021 outputs | 27 June 2022 | Decision by the Office for Statistics Regulation on designation of National Statistics status for Census 2021 outputs | Successfully completed
Update Census 2021 outputs webpages ready for first release | 24 May 2022 | Release plans and product information related to Census 2021 first results is published on website | Successfully completed
Census outputs consultation | July to October 2021 | Consulting with the public for feedback on our proposals for the design and release of Census 2021 data and analysis. | Successfully completed
Publish draft of the outputs schedule | July 2021 | We publish a draft timetable of the various outputs of data from the census.⁷ | Successfully completed
Census Coverage Survey | May to June 2021 | We conduct a short survey to find out how many people we have missed and how many people have been counted more than once in the census. | Successfully completed
Census Field Operation | March to May 2021 | The census field force are deployed to visit people who have not yet responded, to offer help and encourage people to take part. | Successfully completed
Census Day | Sunday 21 March 2021 |  | Successfully completed
Census letters sent to all households and communal establishments | February 2021 – Communal establishments, March 2021 – Households | Start dates for mailing out paper contact materials | Successfully completed
Field force ready for deployment | March 2021 | All our field force staff complete their training and are ready for deployment | Successfully completed
Census operationally ready | February 2021 | Everything in place ready to start census collection | Successfully completed
Census end-to-end testing | November 2020 to January 2021 | The final major testing period for all census collection systems | Successfully completed
Census 2021 webinar series | November to December 2020 | Sharing our plans and providing opportunities to ask questions and give feedback.⁶ | Successfully completed
Operational planning response to the coronavirus (COVID-19) | October 2020 | The potential impacts of the coronavirus (COVID-19) pandemic for Census 2021 and the design changes and contingency plans made in response.⁵ | Successfully completed
Statistical Design for Census 2021 | October 2020 | The end to end statistical design for Census 2021 is published³ alongside a summary overview.⁴ | Successfully completed
Census processing and outputs rehearsal evaluation | August 2020 | An internal evaluation of the processing and output rehearsal | Successfully completed
Census processing and outputs rehearsal | July 2020 | A test of the processing and outputs channels at scale | Successfully completed
Census Regulations in force | June 2020 | Delivering the legislative process | Successfully completed
Census Collection rehearsal and evaluation | February 2020 | A public facing test of the online and paper channels, and field force, at scale. An evaluation of the rehearsal will be published.² | Successfully completed