## Sheet1
Project Name | Census & Data Collection Transformation Programme
Department | ONS
IPA Delivery Confidence Assessment (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the IPA Annual Report on Major Projects) | Amber
Description / Aims | The Census and Data Collection Transformation Programme will run from 2015 to 2025 and has been segmented into four clear objectives: - Delivery of the 2021 Census: research, development, implementation and operation of a 2021 online Census. - Transformation of ONS' Business and Social Surveys, moving to predominantly on-line collection. - Integrated population statistics outputs: developing and implementing methods for enhancing 2021 outputs and producing new outputs before 2021. - Transform the regular delivery of ONS statistics through greater use of non-survey data and use of online collection techniques to make data available more frequently and granularly to support decision-making in the UK
Departmental commentary on actions planned or taken on the IPA RAG rating. | The focus of the programme remained on readiness for on-boarding suppliers and completing service integration activities with the bulk of supplier contracts expected to be signed by the end of 2018. Work continued on Service Integration preparations including a Service Integration Partner procurement and starting the recruitment of a Service Integration Manager who should be in post by the end of 2018. A Head of Test role is also being recruited for the end of 2018 and will be responsible for refining the initial test plan once in post. The White paper has been drafted and reviewed both internally and with Ministers. The programme will continue to carry a level of risk but all key challenges have associated action plans and risk mitigation strategies in place. Programme successes include strengthening the Senior Leadership team with two new permanent members of staff in the roles of Programme Director and Head of Service Design and Management; completing version 1.0 of the Service Design; agreeing approaches to incident and supplier management; deploying a new ‘Field Work Management Tool’ (FWMT) for staff outside the office interviewing in the Social Survey area and ensuring there is a dedicated development team in place to support the Census Rehearsal.
Project - Start Date (Latest Approved Start Date) | 2015-01-01
Project - End Date (Latest Approved End Date) | 2025-03-31
Departmental narrative on schedule, including any deviation from planned schedule (if necessary) | Tranche delivery on schedule.
2018/19 TOTAL Baseline £m (including Non-Government costs) | 94
2018/19 TOTAL Forecast £m (including Non-Government costs) | 89.5
2018/2019 Variance %age | -4.787%
Whole Life Cost TOTAL Baseline £m (including Non-Government costs) | 906.5
Departmental narrative on budget/forecast variance for 2018/19 (if variance is more than 5%) | Budget variance less than 5%
Departmental Narrative on Budgeted Whole Life Costs | The costs provided reflect Census Transformation; Data Collection Transformation and Digital Transformation costs; aligned to the Programme Business Case v2.0 approved by HM Treasury on 16th October 2017, comprising 3 main strands: 1) Census Transformation Programme 2) Data Collection Transformation Programme 3) Digital Transformation Costs are expressed in nominal terms.
Annual Report Category | Government Transformation and Service Delivery
The IPA Annual Report publishes the whole life cycle costs on projects, based on figures from their Business Cases, whilst the National Infrastructure and Construction Pipeline (NICP) focuses primarily on the upfront capital investment on a project. Where both documents refer to the same projects, this distinction will be the principal reason for any differences in the data sets published. Other government publications may use different methodologies to derive cost figures